## Slide 1: Education and Public Outreach
Laura Whitlock
Sonoma State University

## Slide 2: Team Members
Sonoma State University
  Laura Whitlock, Lynn Cominsky
Penn State University
  Lisa Brown, Eric Feigelson
Goddard Space Flight Center
  Padi Boyd, Alan Smale, Karen Smale
Coordinated Efforts in Italy and UK
Swift Education Committee (SwEC)
  Barbara Crawford (PSU, Chair); Bruce Hemp, Tom Arnold, Scot Weigert (Master Teachers); Paul Roche (UK); Joan Sanders (AESP); Isabel Hawkins (UCB); Margaret Chester (PSU); Ann Parsons (GSFC); Jim Lochner (GSFC)

## Slide 3: Team Members
Subcontracts
  Lawrence Hall of Science
    Key Personnel: Alan Gould
  Videodiscovery, Inc.
    Key Personnel: Shaun Taylor
  What’s in the News?
    Key Personnel: Katie O’Toole
  WestEd
    Key Personnel: Kristin Hershbell, Steve Schneider

## Slide 4: Overview of Program Components
GEMS Guide
Educator Training
  Appalachian Region Project
  North Bay Science Project
  Conventions, workshops, etc
Web Materials, Quest Chats, Space Mystery Module
What’s in the News? programs
Curriculum materials
Evaluation

## Slide 5: GEMS Guide
Initial meeting between LHS and SSU personnel, May 2000
“Way Beyond the Rainbow” working title
Subcontract in place between SSU and Lawrence Hall of Science, October 2000
Tentative schedule
  Draft #1 completed by Summer 2001
  Local field testing Fall 2001
  Draft revisions completed Summer 2002
  National Field Testing Fall 2002
  Final release Summer 2003

## Slide 6: Educator Training
Appalachian Region Project
  Swift materials included during Summer 2000
  ~ 25 participants
  Role of materials will expand over next few years
North Bay Science Project
  Swift materials included during Summer 2000
  ~ 30 participants
  Role of materials will expand over next few years

## Slide 7: Educator Training
Conventions, Workshops - “High Energy Bursts of Math & Science”
  NSTA, April 2000 (Orlando, 20 participants)
  NCTM, April 2000 (Chicago, 30 participants)
  CSTA, Oct 2000 (Sacramento, 28 participants)
  HEAD, Nov 2000 (Honolulu, 35 participants)
Next Year Conventions, Workshops - “Light Up the Universe”
  NSTA, March 2001, St. Louis
  NCTM, April 2001, Orlando
  CSTA, Oct 2001 (Short Course, workshop), Palm Springs
  CMC, Dec 2001, Asilomar

## Slide 8: Web Materials
Web Site
  Swifty Bits
  Cosmic Lottery
NASA Quest Chats
  1st one held in Sept 2000
  One a month, alternating with GLAST

## Slide 9: Web Materials
Space Mystery Module - 2003
A deep space traveler
awakes from the flight-freezer
when a long-range sensor sounds
the alert for a dangerous
environment. You must
discover what is happening and
what course of action to take.
Currently working on 3 other
Mystery Modules with Videodiscovery
as part of NASA’s LEARNERS program

## Slide 10: What’s in the News?
First segment introducing Swift and the EM spectrum is scheduled to be completed in Jan 2001

## Slide 11: Curriculum Materials
Theme for 2001 is “Waves and Wave Motion”
  Who’s Got the Power? - a deck of cards and activities to reinforce scientific notation, units, and astronomy concepts

## Slide 12: Curriculum Materials
  • Spin a Spectrum - use our
  EM spectrum wheel to
  help you solve a series
  of mysteries
  and riddles based
  on content topics
  in the National Science
  and Mathematics
  Standards

## Slide 13: Curriculum Materials
  • Catch the Wave - a Swift slinky and series of classroom activities and lessons will teach the fundamentals of waves

## Slide 14: Curriculum Materials
Theme for 2002 is “Forces & Motions”
Theme for 2003 is “Interactions of Energy and Matter”
After launch, we will focus on interpretation of results --depending on what they are and how the discoveries fit into the National Science and Math Standards

## Slide 15: Evaluation
Contract recompeted Spring/Summer 2000
WestEd selected; subsequently selected for GLAST evaluation as well, resulting in a cost savings to both missions.
Subcontract between SSU and West Ed established Nov 2000
Draft teacher survey completed

## Slide 16: Conclusion
Swift E/PO on track
All subcontracts in place, all contacts established, SwEC membership filled
First educator workshops done in 2000
First new materials scheduled to come out early 2001
Long-term plan established